## Sheet1
Sprint Number and Feature | Task | Hours
1 - MVP | Planning Session - Sprint 1[MVP] | 9
1 | Set up Fors Replacement project(SimonConnect) structure with Git integration | 12
1 | Provide UI with a PDF Button to allow PDFs to be uploaded | 20
1 | Logic to convert uploaded PDF to Excel and upload to a file share as a comma delimited text file accessible by Simon | 40
1 | Validation and Unit Tests | 30
1 | Demo Application | 9
2 - CMS | Planning Session - Sprint 2 | 9
2 | Provide Listing Page with all uploaded PDFs, allowing PDFs to be deleted and re-uploaded. Listing page will contain Title, Upload Date and Converted Excel Details | 40
2 | Provide a Details page to display Excel file, with option to delete Excel File and Re-upload it with modifications and reupload it as a comma delimited text file accessible by simon | 32
2 | Validation and Unit Tests | 30
2 | Demo Application | 9
| Total: | 240